## Slide 1
Time since first referral to first paediatric assessments
North Tees & Hartlepool NHS Foundation Trust​ RCPCH Epilepsy Quality Improvement Programme project team:
Dr Beena Kurup, Consultant Paediatrician
Dr P Siva Kumar, Consultant Paediatrician, Lead Epilepsy Service
Dr A Koshy, Consultant Paediatrician
Pauline King, Epilepsy Specialist Nurse
Katie Bailey, Epilepsy Specialist Nurse
National audit results included within this case study acts as a guide only to performance standards. The service improvements made during the EQIP cannot be entirely attributed to the reported results in the Epilepsy12.
RCPCH Epilepsy Quality Improvement Programme
August 2021 – April 2022

## Slide 2: Time since first referral to first paediatric assessments - North Tees & Hartlepool NHS Foundation Trust​
Project aim:
To reduce waiting times for new seizure referrals by a paediatrician with expertise in epilepsy from 16 weeks to 4 weeks in 50% of referrals within 6 months of the project start by the end of March 2022.
Background:
According to Epilepsy12 data, 31% of their patients were waiting more than 16 weeks for their first seizure appointment with a paediatrician with expertise in epilepsy. The majority of referrals were from GPs and outpatient departments, which is an unusual proportion compared to other services in the country and required detailed analysis.
Area of focus:
To focus on new referrals and improve the time from the first seizure to the first appointment. The team plans to map the patient referral pathways and implement what they have learned from the RCPCH Equality Quality Improvement Programme to begin making the required changes in service provision.

## Slide 3: Time since first referral to first paediatric assessments - North Tees & Hartlepool NHS Foundation Trust​
Improving access to Epilepsy services & thereby Patient Experience. Ensuring patients are seen timely by reducing current waiting time of 16 weeks.
To see 50 % of referrals in 4 weeks by March 2022
Primary Drivers
Secondary Drivers
Improve patient experience
Review existing process
Ensure Clear pathway
Ensure parent patient participation and incorporate their views into changes
Create SOP/ guidelines/policies; Disseminate information
Streamline referral process
Driver Diagram
Change ideas
1. Map Patient journey following referrals ( GP, Ward, A&E, OPD).
2. Identify problem areas for delays
3. Brainstorm for solutions.
4. Identify Stakeholders
5. Streamline referral pathways. Have one point of referral for GP and internal referrals.
6. Test the process and identify if improving and implement change.
7. Patient & family engagement, incorporate feedback into solutions.
8. Dissemination of information/change within the department and wider settings
9. Audit of the process & Pathways regarding time frame seen and make changes.
10. Achieve 50% of this by March 2022

## Slide 4: Time since first referral to first paediatric assessments - North Tees & Hartlepool NHS Foundation Trust​
Changes:
After joining the EQIP, the team recognised their aim to reduce referral waiting times in line with NICE recommendations of 2 weeks was not achievable within the programme period; therefore, the objective changed to reduce waiting times to 4 weeks in 50% of referrals.
As an initial step, it was agreed to standardise templates for clinics for uniformity purposes.
Researched from neighbouring Trusts, the different types of epilepsy clinic templates that include a standard time frame for new patient clinic appointment time and similarly for the reviews. Each Trust had different types of templates that ranged from 1-hour appointment times for a new patient to 30 minutes. The team agreed to standardise their template with three new patient slots (45 minutes each) and five review slots with 20 minute slots (total clinic time: 4 hours).
Arrangements were made with the appointment booking office to leave a single new patient slot per epilepsy clinic for up to 48 hours so that any urgent referrals can be booked into the clinics at short notice. If no new patients are booked in less than 48 hours, the booking office can use the slots to book review patients. This meant that between the three consultants, there would be a maximum of three new patient slots free to book referrals.
Revised the current pathway for referral to epilepsy clinics for patients admitted to the ward from A&E, which is now processed by the booking office, and patients are offered the next available new patient slot.

## Slide 5: Time since first referral to first paediatric assessments - North Tees & Hartlepool NHS Foundation Trust​
Changes:
Created a Standard Operating Procedure (SOP) for A&E referrals of afebrile seizure patients to be seen in seizure clinics, and this is now functional.
Developed a service improvement proposal for leaving one new patient appointment free to ensure patients are seen urgently.

## Slide 6: Time since first referral to first paediatric assessments - North Tees & Hartlepool NHS Foundation Trust​
Results:
Established a single referral pathway.
Allocating referrals to the next available space rather than to the same consultant.
Implemented a single process of appointment allocation by standardising templates for clinics to have uniformity and streamlining GP referrals.
The team managed to work on resolving the issues, which has led to an increase in one or two additional new patients.
Experienced changes in reduced waiting times for new patients referred via the GP.
Measured and reviewed progress weekly, which revealed for the first time that they had achieved their aim of reducing waiting times from 16 to 4 weeks for 50% of patients.
A patient was added to a new patient appointment from a referral completed on 23/10/21. This meant the patient was seen in 3 weeks; however, it was seen as an extra, which is not ideal.
Conducted a brief audit on whether the changes were made and had an impact on reducing the delay in seeing patients.

## Slide 7: Time since first referral to first paediatric assessments - North Tees & Hartlepool NHS Foundation Trust​
Results:
Increased patient and parent engagement, which helped to understand the issues experienced when requesting their feedback on required improvements from a different perspective.
Selected four patients to provide feedback on the changes made:
  Patient A (7 weeks)” Quite happy with the way it was turned around."
  Patient B (4 weeks) “Experience was really good. Wait, okay. Consultant was excellent”.
  Patient C (4 weeks) “Quite alright as it gave us time to digest what had happened. Any sooner would have been too much information.”
  Patient D (4 weeks) “Very impressed with the waiting time; I thought it would be much longer. We already have the next appointment too.”
Incorporated sustainable improvement by implementing a review process for all clinic appointment allocation compliance 48 hours before each clinic.

## Slide 8: Time since first referral to first paediatric assessments - North Tees & Hartlepool NHS Foundation Trust​
Change implemented
Time Referrals seen
The team reviewed the month prior to the implementation of the change (August) to get a baseline of where they were in terms of NICE guidelines. The review showed that the average waiting time was 12 weeks before the first appointment..

## Slide 9: Time since first referral to first paediatric assessments - North Tees & Hartlepool NHS Foundation Trust​
Chart: 
| August | September | October | November | December
Time in weeks from referral to first appointment | 12 | 9 | 6 | 4 | 4
The team collected data from two random new patients seen in two of the consultant clinics for the months following, up until December. The waiting time of each patient was compared and then calculated against the average waiting time for that month.

## Slide 10: Audit results cohort 3/4 – Professional input - North Tees & Hartlepool NHS Foundation Trust​
NICE recommends that children and young people presenting with suspected seizure are seen by a specialist in the diagnosis and management of epilepsies within 2 weeks of presentation (Quality statement 1).
Percentage of CYP with input from:​ | 2019​ | 2020​ | 2021​ | 2022​ | 2021 – PENNEC​ | 2021 – England & Wales​ | 2022 – PENNEC​ | 2022 – England & Wales​
Paediatrician with expertise OR paediatric neurologist (PI.1)​ | -​ | 81%​ | 85%​ | 63%​ | 81%​ | 88%​ | 88%​ | 91%​
Paediatrician with expertise​ | -​ | 90%​ | 88%​ | 63%​ | 77%​ | 85%​ | 85%​ | 89%​
Paediatric neurologist​ | -​ | 12%​ | 24%​ | 16%​ | 27%​ | 25%​ | 19%​ | 20%​
Epilepsy specialist nurse​ | -​ | 88%​ | 82%​ | 63%​ | 64%​ | 80%​ | 75%​ | 80%​
The percentage of CYP with input from a paediatrician with expertise in the first year of care in 2021 was 88% in 2021 above regional and national averages and 63% in 2022.

## Slide 11: Audit results cohort 3/4 - Time since first referral - North Tees & Hartlepool NHS Foundation Trust​
The percentage of children and young people diagnosed with epilepsy that were seen by a paediatrician with expertise in epilepsy within 2 weeks in 2021 was 21%. In 2022 this percentage reduced to 5%.
Time since first referral to first paediatric assessment​ | 2019​ | 2020​ | 2021​ | 2022​ | 2021 -PENNEC​ | 2021- England & Wales​ | 2022 – PENNEC​ | 2022 – England & Wales​
0 – 2 weeks​ | -​ | 10%​ | 21%​ | 5%​ | 22%​ | 23%​ | 20%​ | 21%​
2 – 4 weeks​ | -​ | 7%​ | 9%​ | 0%​ | 10%​ | 12%​ | 11%​ | 11%​
4 – 6 weeks​ | -​ | 12%​ | 9%​ | 0%​ | 8%​ | 9%​ | 9%​ | 11%​
6 – 8 weeks​ | -​ | 2%​ | 6%​ | 11%​ | 5%​ | 7%​ | 6%​ | 8%​
8 – 10 weeks​ | -​ | 7%​ | 0%​ | 16%​ | 2%​ | 5%​ | 7%​ | 7%​
10 – 12 weeks​ | -​ | 7%​ | 12%​ | 5%​ | 4%​ | 3%​ | 4%​ | 5%​
12 – 14 weeks​ | -​ | 5%​ | 3%​ | 11%​ | 2%​ | 3%​ | 4%​ | 3%​
14 – 16 weeks​ | -​ | 2%​ | 3%​ | 0%​ | 1%​ | 2%​ | 1%​ | 2%​
16 + weeks​ | -​ | 31%​ | 24%​ | 16%​ | 15%​ | 13%​ | 16%​ | 1%​
The percentage of children and young people diagnosed with epilepsy that were seen by a paediatrician with expertise in epilepsy at +16 weeks has decreased in 2021 to 24% and continued to reduce to 16% in 2022 .

## Slide 12: Audit results cohort 3/4 - Time since first referral - North Tees & Hartlepool NHS Foundation Trust​
Chart: Time since first referral to first paediatric assessment
| 2020 | 2021 | 2022
0-4 weeks | 0.17 | 0.3 | 0.05
4-8 weeks | 0.14 | 0.15 | 0.11
8-12 weeks | 0.14 | 0.12 | 0.21
12-16 weeks | 0.07 | 0.06 | 0.11
>16 weeks | 0.31 | 0.24 | 0.16
Graph showing time since first referral to first paediatric assessment between the years 2020-2022.

## Slide 13: Audit results cohort 3/4 - Time since first referral - North Tees & Hartlepool NHS Foundation Trust​
Chart: Time since referral to first paediatric assessment in 2022
| RVW | PENNEC | England & Wales
0-4 weeks | 0.05 | 0.31 | 0.32
4-8 weeks | 0.11 | 0.15 | 0.19
8-12 weeks | 0.21 | 0.11 | 0.12
12-16 weeks | 0.11 | 0.05 | 0.05
>16 weeks | 0.16 | 0.16 | 0.13
The percentage of CYP waiting less than 4 weeks from first referral to first paediatric assessment has decreased since 2021. * RVW represents Trust level results for North Tees & Hartlepool NHS Trust

## Slide 14: Time since first referral to first paediatric assessments - North Tees & Hartlepool NHS Foundation Trust​
Challenges:
The engagement with the booking office regarding updating vetting procedures for referrals that require written approval of suggested changes for booking into new patient slots with any consultant was resolved.
The team identified that many referrals were addressed to named consultants, which resulted in some receiving a lot more referrals than others. This is because the GPs are aware of the consultants who have been in the post longer than others. This meant that for those consultant clinics, they had no new patient slots for several weeks due to slots being filled with referrals, resulting in 12–16 week wait times compared to other consultants, who had clinic slots with 3–4 week wait times.
Created awareness amongst colleagues by presenting their EQIP project to the Trust Directorate meeting to express the importance of help from management and the benefits of support from a Quality Improvement Project Manager. Unfortunately, although management was in agreement, the team was not given any additional dedicated time to work on the project, despite the assured support.
It was identified that new patient slots were often booked for review patients, which meant that new patient appointments were given several weeks down the line.

## Slide 15: Time since first referral to first paediatric assessments - North Tees & Hartlepool NHS Foundation Trust​
Outcomes:
Mapped new referral pathways to successfully identify gaps and inconsistencies in the process for first seizure patients.
Measured and reviewed progress weekly, which revealed for the first time that they achieved their aim of reducing waiting times from 16 to 4 weeks for 50% of patients during the participation of the EQIP.
Tested and established a new single referral pathway from GP, A&E, and in-patient wards.
Tested and approved the new standardisation of appointment time allocations for new and review patients.
Experienced changes in reduced waiting times for new patients referred via the GP.
Increased engagement with patients and families helped the team learn about issues experienced from their perspective.
Patient engagement based on their experience of wait times informed the team they were:
  Generally positive.
  Happy with telephone communication.
  Information overload if an appointment is received in 2 weeks.
  Internal referrals: happy to wait if contact numbers are provided.
  Referrals from GP’s: expressed anxiety in the wait.

## Slide 16: Time since first referral to first paediatric assessments - North Tees & Hartlepool NHS Foundation Trust​
Outcomes:
National audit outcomes showed the percentage of CYP with input from a paediatrician with expertise in the first year of care in 2021 was 88%, above regional and national averages. In 2022 this figure was 63%.
The percentage of children and young people diagnosed with epilepsy that were seen by a paediatrician with expertise in epilepsy within 2 weeks in 2021 was 21%. In 2022, this percentage reduced to 5%.
The percentage of children and young people diagnosed with epilepsy that were seen by a paediatrician with expertise in epilepsy at +16 weeks has decreased in 2021 to 24% and continued to reduce to 16% in 2022.

## Slide 17: Time since first referral to first paediatric assessments - North Tees & Hartlepool NHS Foundation Trust​
Lessons learnt
Constancy of purpose is key.
Continuously engaging with all parts of the service and each element of the process is fundamental.
Patient and family engagement and feedback helped drive the changes required.
Communicating any new changes to all parts of the system is essential to ensuring sustained improvement in sharing best practices and internal practices.
Formal use of QI tools, such as mapping the patient’s journey, helped to identify gaps, drive change, and measure progress.
Direct contact with parents and families was a fast way to gather feedback regarding their experience of the process and the changes made.
An important aspect of any improvement plan is to identify how they can improve patient participation and engagement and incorporate patient views into future improvement projects.
Visual presentation of team project intervention
Team poster
Team video presentation

## Slide 18: https://eqip.rcpch.ac.uk
@RCPCHEQIP
eqip@rcpch.ac.uk